**Annual Implementation Plan - 2021**

**Define Actions, Outcomes and Activities**

Kurunjang Primary School (5256)



Submitted for review by Jennifer Robinson (School Principal) on 18 December, 2020 at 11:36 AM
Endorsed by Tony Simpson (Senior Education Improvement Leader) on 22 January, 2021 at 05:14 PM
Endorsed by Elizabeth Bajada (School Council President) on 09 March, 2021 at 12:32 PM

**Define Actions, Outcomes and Activities**

|  |  |
| --- | --- |
| Goal 1 | 2021 Priorities Goal |
| 12 Month Target 1.1 | By the end of 2021:Learning, catch up and extension:PAT Maths- Year 2-6- increase the percentage of students achieving greater than 12 months growth from 10% to 20%Decrease the percentage of students achieving less than 12 months growth from 19% to 11%PAT Reading-Year 2-6- Increase the percentage of students achieving greater than 12 months growth from 5% to 20%Decrease the percentage of students achieving less than 12 months growth from 26% to 18%Happy, Active and Healthy Kids:Improve the positive endorsement for the AToSS factors:Student voice and Agency from 56% to 70%Teacher and student relations- teacher concern from 69% to 80%Connected Schools:Improve the positive endorsement for the AToSS factors:Sense of connectedness from 66% to 77%Improve the positive endorsement for the SOS factors:Understanding formative assessment from 54% to 70%Understanding curriculum from 61% to 78% |
| KIS 1Curriculum planning and assessment | Learning, catch-up and extension priority |
| **Actions** | - Develop and implement the Professional Learning Community improvement cycle for differentiated learning in collaboration with the Differentiated Support for School Improvement team.- Increase teacher capacity to embed the KPS literacy and numeracy instructional model and high impact teaching strategies. - Embed consistent approach to formative assessment and develop data literacy of teachers to inform understanding of student needs and progress. - Establish and implement DET Tutoring initiative for differentiated support of students in literacy and numeracy. |
| **Outcomes** | Leaders will:- support teachers to consistently and explicitly plan and implement the KPS instructional model and evidenced based high impact teaching strategies.- lead regular update of data walls informed by student assessment data.- identify students and cohorts in need of targeted academic support or intervention.- establish intervention/small group in class and withdrawal tutoring.Teachers will:- confidently and accurately identify learning needs of their students.- engage in reflective practice, evaluate and plan curriculum, assessments, and lessons within the PLC improvement cycle.- incorporate HITS (Differentiated teaching, Setting Goals, Feedback and Questioning) to plan units and lessons.- provide regular feedback and monitor student progress using data walls.Students will: - know how lessons are structured and how this supports their learning.- work at their level using differentiated resources and intervention.- receive regular feedback in their learning and know what their next steps/goals are to progress. |
| **Success Indicators** | Leaders:- Documented Improvement cycle within curriculum unit and lesson planning.- Classroom observations and learning walks; and notes from coaching conversations.- Leadership and SIT meeting minutes.- Documented tutoring model and timetable.Teachers:- Formative assessment data and teacher judgement data.- Notes of Peer Observations and coaching conversations.- Differentiated curriculum documents and evidence of student learning at different levels .- Data walls indicating clear student progress.Students:- Articulated progress against Individual Learning Plan goals.- Student feedback on differentiation, the instructional model, and use of common strategies. |
| Activities and Milestones | Who | Is this a PL Priority | When | Budget |
| Design and deliver professional learning on formative assessment and collecting, moderating, analysing, responding to and monitoring data throughout the year. | 🗹 School Leadership Team | 🗹 PLP Priority | from:Term 1to:Term 4 | $10,000.00🗹 Equity funding will be used |
| Align the DSSI theory of action document with the 2021 AIP goals and Key Improvement Strategies. | 🗹 Leadership Partners (DSSI)🗹 School Leadership Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Establish processes/structures for coaching/mentoring and observation of the KPS instructional model and high impact teaching strategies. | 🗹 Leading Teacher(s)🗹 Learning Specialist(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $20,000.00🗹 Equity funding will be used |
| Incorporate instructional practice and high impact teaching strategies focus into teachers' Performance and Development plans. | 🗹 Teacher(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Appoint equivalent EFT 3.6 tutors for 12 months.  | 🗹 Principal | 🞎 PLP Priority | from:Term 1to:Term 1 | $279,000.00🗹 Equity funding will be used |
| Establish criteria for identifying students requiring individual and tailored support, tutoring and intervention; and develop a model and and schedule times for support/tutoring to occur. | 🗹 Teaching and Learning Coordinator | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| KIS 2Health and wellbeing | Happy, active and healthy kids priority |
| **Actions** | - Embed the KPS Engagement model for social-emotional learning, and student engagement and inclusion.- Refine classroom Key Learning Areas to prioritize Social and Emotional Learning (SEL) cognitive and behavioural skills, and physical exercise and relaxation.- Build staff capacity to collect, analyse, monitor and respond to student engagement data.- Build relationships and engage with all students and families; and ensure all students know there is someone who cares about them. |
| **Outcomes** | Leaders will:- enhance strong school and community culture and values.- embed wellbeing supports and positive support planning (PSP) for students and families.- identify at risk and vulnerable students and provide targeted support in conjunction with teaching staff in a timely manner.Teachers will:- incorporate SWPBS, BSEM, AVID and Respectful Relationships practices and strategies in planning units of work.- consistently use and model agreed routines and practices for student engagement and inclusion.- provide regular communication and support/monitoring to all students and families.Students will:- develop strong relationships with peers.- demonstrate strategies and behaviors for self awareness and regulation. |
| **Success Indicators** | Leaders:- Documented Engagement strategies within curriculum unit and lesson planning.- Classroom observations and learning walks focusing on positive classroom climate; and notes from coaching conversations.- Wellbeing and SIT meeting minutes.- Documented PSP (positive support planning) model and timetable.Teachers:- Visual representation of KPS engagement model visible in classrooms. - Anecdotal, COMPASS and attendance data.- Refine documentation of referrals and communication process regarding monitoring and escalating wellbeing concerns via issue tracker.- Notes of Peer Observations of Positive Climate routines and practices.- Lesson planning reflecting SEL curriculum, health and physical activity.Students:- Co- constructed classroom anchor charts and visuals of expected behaviors and AVID strategies.- participation in emotional regulation strategies such as brain breaks, rhythmic, repetitive activity. |
| Activities and Milestones | Who | Is this a PL Priority | When | Budget |
| Develop curriculum units of social, emotional learning and respectful relationships collaboratively within teams.  | 🗹 Leading Teacher(s) | 🗹 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Establish "Healthy minds & bodies" after-school club. | 🗹 Student Wellbeing Co-ordinator🗹 Wellbeing Team  | 🞎 PLP Priority | from:Term 2to:Term 4 | $0.00🞎 Equity funding will be used |
| Refine roles and responsibility of teachers, education support staff and middle leaders for establishing and maintaining positive relationships with all students and families. | 🗹 Assistant Principal🗹 Principal | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Embed clear referral processes for identifying at risk and vulnerable students. | 🗹 Assistant Principal🗹 Wellbeing Team  | 🞎 PLP Priority | from:Term 1to:Term 2 | $0.00🞎 Equity funding will be used |
| Establish a rostered process for regular check-ins with all families. | 🗹 All Staff | 🞎 PLP Priority | from:Term 1to:Term 2 | $0.00🞎 Equity funding will be used |
| KIS 3Building communities | Connected schools priority |
| **Actions** | - Strengthen and embed the school-wide approach for communication with parents/carers/kin, incorporating the effective ways in which KPS connected during flexible and remote learning.- Build staff capability to integrate digital learning.- Celebrate the multiculturalism of the KPS community. |
| **Outcomes** | Leaders will:- Develop a plan for increasing the engagement of parents/carers/kin or community groups that are under-represented or harder to reach.Teachers will:- be confident to integrate digital learning tools and strategies.- have strong relationships with students and parents/carers.Students will: - feel as though they belong and are known.- feel connected to school and have positive attitudes to school and attendance. |
| **Success Indicators** | Leaders:- Updated documentation of school digital policy and scope and sequence.- Feedback from Parent/carer/kin ( eg VOX Pops- voice snapshot of the people).Teachers:- Positive endorsements in whole school surveys (SOS, POS).- Digital tools and strategies used to support and enhance learning.- Frequent communications with parents/carers. Students:- Positive endorsements in survey data Years 4-6 (AToSS). |
| Activities and Milestones | Who | Is this a PL Priority | When | Budget |
| Establish school-based Aboriginal and Torres Strait Islander Education and Multicultural community events. | 🗹 Leading Teacher(s)🗹 Learning Specialist(s) | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Provide relevant and timely COMPASS notifications and virtual information to the parent community. | 🗹 Assistant Principal | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |
| Identify digital tools that were successful during flexible and remote learning and how they can continue to be implemented. | 🗹 All Staff | 🗹 PLP Priority | from:Term 1to:Term 2 | $0.00🞎 Equity funding will be used |
| Provide access to and promote information in appropriate community languages and engage translation services. | 🗹 Leadership Team | 🞎 PLP Priority | from:Term 1to:Term 4 | $0.00🞎 Equity funding will be used |